## RACI Matrix
RACI Matrix Template
| Project Leadership |  |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Contributors
| Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5 | Role #1 | Role #2 | Role #3 | Role #4 | Role #5
Initiate Phase Activities
Plan Phase Activities
Execute Phase Activities
Control Phase Activities
Close Phase Activities
Role
Project Deliverable
(or Activity)

## Instructions
Instructional Notes for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion
Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.

## Sample Project
RACI Matrix Template
| Sr. Operating Exec | SL Exec | Hospital SL Ops. Director | Hospital President | Hospital VP | FV Group Practice | UMP | SL Medical Director | SL Executive Committee | Strategy & Marketing VP | SL Marketing Director | Finance | HR | IS | Physician Recruitment | SET | Leadership Council | Legal
Medical Staff Development/Relations
▪ Physician recruitment strategic plan | A | R | C | C | C | C | C | R | C | C | I | C | C | I | C
▪ Physician recruitment plan
▪ Physician recruitment and selection | bar: R
▪ Oncology Physician recruitment and selection* | I | R | C | C | C | C | A | R |  | I | I | I | I | I | R |  |  | C
▪ Mothers/Children Physician recruitment and selection (e.g. Lakes pediatrician)* | I | R | I | C | C | A | C | R |  | I | I | I | I | I | R
▪ Physician development plan
▪ Referral distribution and preferences
▪ Physician marketing resources
Capital
▪ Annual capital plan | [11 empty] | R |  |  |  | A | C | bar: R R R
▪ Annual capital plan (e.g. joint venture) | C | R | C | C | C | I | C | C | R | I | I | R |  |  |  | A | C
▪ Strategic capital prioritization | [8 empty] | R |  |  | C |  |  |  | A | C | bar: I I to R R R
▪ Capital project business plan approval
▪ Capital equipment prioritization
▪ Capital equipment approval
Programming
▪ New services
▪ Existing service expansion, change, contraction
▪ Service hours
▪ Service standards
Planning
▪ System Strategy
▪ Local Strategy
Marketing and Sales (physician liaisons)
▪ Strategy
▪ Tactics
▪ Resources
▪ Resource Distribution
* The accountable party (UMP, FV Group, etc) is the employment home for the physician
Stakeholders/Roles
Key Decisions
or Tasks